## Dashboard
Project Management Dashboard |  |  |  | 17-Feb-22 to 2-Mar-22
Project | Task | Manager | Start Date | End Date | Duration | Days completed | Progress | Budget | Actual
Alpha | Task 1 | McFay | 2022-02-28 | 2022-03-09 | 8 | 3 | 37.5% | 96000 | 32256
| Task 2 | Wood | 2022-03-02 | 2022-03-14 | 9 | 4 | 44.44% | 513000 | 226233
| Task 3 | Ladd | 2022-02-20 | 2022-02-24 | 5 | 3 | 60% | 616000 | 401579
| Task 4 | Hirsch | 2022-02-19 | 2022-02-22 | 3 | 3 | 100% | 817000 | 807069
| Task 5 | Samora | 2022-02-21 | 2022-03-01 | 7 | 3 | 42.86% | 372000 | 173166
| Task 6 | McFay | 2022-02-24 | 2022-03-09 | 10 | 2 | 20% | 50000 | 8400
| Task 7 | Wood | 2022-02-24 | 2022-03-09 | 10 | 3 | 30% | 807000 | 262679
| Task 8 | Ladd | 2022-02-24 | 2022-02-28 | 3 | 0 | 0% | 691000 | 0
Delta | Task 1 | Hirsch | 2022-03-02 | 2022-03-14 | 9 | 8 | 88.89% | 787000 | 727188
| Task 2 | Samora | 2022-03-02 | 2022-03-15 | 10 | 2 | 20% | 228000 | 47880
| Task 3 | McFay | 2022-02-17 | 2022-02-22 | 4 | 0 | 0% | 147000 | 0
| Task 4 | Wood | 2022-02-19 | 2022-03-01 | 8 | 5 | 62.5% | 338000 | 205123
| Task 5 | Ladd | 2022-02-24 | 2022-03-09 | 10 | 3 | 30% | 857000 | 305949
| Task 6 | Hirsch | 2022-02-25 | 2022-03-06 | 6 | 3 | 50% | 602000 | 322371
| Task 7 | Samora | 2022-02-25 | 2022-03-02 | 4 | 2 | 50% | 990000 | 451440
Gemini | Task 1 | Hirsch | 2022-02-17 | 2022-02-23 | 5 | 2 | 40% | 218000 | 97337
| Task 10 | Ladd | 2022-02-24 | 2022-03-03 | 6 | 3 | 50% | 416000 | 175015
| Task 2 | Samora | 2022-02-17 | 2022-02-24 | 6 | 3 | 50% | 393000 | 177440
| Task 3 | McFay | 2022-02-18 | 2022-03-03 | 10 | 4 | 40% | 86000 | 31046
| Task 4 | Wood | 2022-02-21 | 2022-03-03 | 9 | 3 | 33.33% | 732000 | 261324
| Task 5 | Ladd | 2022-02-17 | 2022-02-22 | 4 | 1 | 25% | 492000 | 116850
| Task 6 | Hirsch | 2022-02-20 | 2022-02-27 | 6 | 0 | 0% | 188000 | 0
| Task 7 | Samora | 2022-02-20 | 2022-02-28 | 7 | 3 | 42.86% | 180000 | 79380
| Task 8 | McFay | 2022-02-24 | 2022-03-02 | 5 | 2 | 40% | 582000 | 195231
| Task 9 | Wood | 2022-02-24 | 2022-03-08 | 9 | 1 | 11.11% | 562000 | 74746
Orion | Task 1 | Hirsch | 2022-02-18 | 2022-02-28 | 7 | 7 | 100% | 293000 | 273001
| Task 10 | Ladd | 2022-02-17 | 2022-02-21 | 3 | 3 | 100% | 68000 | 64987
| Task 2 | Samora | 2022-02-17 | 2022-03-01 | 9 | 4 | 44.44% | 224000 | 57910
| Task 3 | McFay | 2022-02-18 | 2022-03-01 | 8 | 0 | 0% | 978000 | 0
| Task 4 | Wood | 2022-02-20 | 2022-02-28 | 7 | 3 | 42.86% | 932000 | 379157
| Task 5 | Ladd | 2022-02-21 | 2022-02-24 | 4 | 1 | 25% | 854000 | 322812
| Task 6 | Hirsch | 2022-02-21 | 2022-02-28 | 6 | 3 | 50% | 81000 | 38461
| Task 7 | Samora | 2022-02-24 | 2022-03-03 | 6 | 5 | 83.33% | 169000 | 136468
| Task 8 | McFay | 2022-02-25 | 2022-03-02 | 4 | 1 | 25% | 61000 | 12078
| Task 9 | Wood | 2022-02-27 | 2022-03-07 | 7 | 3 | 42.86% | 645000 | 273048
Vega | Task 1 | Hirsch | 2022-02-17 | 2022-03-02 | 10 | 5 | 50% | 839000 | 406974
| Task 2 | Samora | 2022-02-21 | 2022-02-27 | 5 | 4 | 80% | 729000 | 487139
| Task 3 | McFay | 2022-02-24 | 2022-03-06 | 7 | 3 | 42.86% | 826000 | 298186
| Task 4 | Wood | 2022-02-26 | 2022-03-07 | 7 | 2 | 28.57% | 895000 | 280583
| Task 5 | Ladd | 2022-02-28 | 2022-03-02 | 3 | 2 | 66.67% | 341000 | 129785
Grand Total | [7 empty] | 19695000 | 8340291
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Workings
Not Started | In Progress | Completed | Remaining | Total Tasks | Values
4 | 33 | 3 | 37 | 40 | Sum of Days completed | 112 | Days Completed | 42.11% |  | Actual | Budget
[5 empty] | Sum of Duration | 266 | Days Remaining | 57.89% | Bar Chart | 8340291 | 19695000
[9 empty] | Donut Chart | 42.35% | 57.65%

## Dataset
Project | Task | Manager | Start Date | Duration | End Date | Days completed | Progress | Budget | Actual
Gemini | Task 1 | Hirsch | 2022-02-17 | 5 | 2022-02-23 | 2 | 40% | 218000 | 97337
Gemini | Task 2 | Samora | 2022-02-17 | 6 | 2022-02-24 | 3 | 50% | 393000 | 177440
Gemini | Task 3 | McFay | 2022-02-18 | 10 | 2022-03-03 | 4 | 40% | 86000 | 31046
Gemini | Task 4 | Wood | 2022-02-21 | 9 | 2022-03-03 | 3 | 33.33% | 732000 | 261324
Gemini | Task 5 | Ladd | 2022-02-17 | 4 | 2022-02-22 | 1 | 25% | 492000 | 116850
Gemini | Task 6 | Hirsch | 2022-02-20 | 6 | 2022-02-27 | 0 | 0% | 188000 | 0
Gemini | Task 7 | Samora | 2022-02-20 | 7 | 2022-02-28 | 3 | 42.86% | 180000 | 79380
Gemini | Task 8 | McFay | 2022-02-24 | 5 | 2022-03-02 | 2 | 40% | 582000 | 195231
Gemini | Task 9 | Wood | 2022-02-24 | 9 | 2022-03-08 | 1 | 11.11% | 562000 | 74746
Gemini | Task 10 | Ladd | 2022-02-24 | 6 | 2022-03-03 | 3 | 50% | 416000 | 175015
Orion | Task 1 | Hirsch | 2022-02-18 | 7 | 2022-02-28 | 7 | 100% | 293000 | 273001
Orion | Task 2 | Samora | 2022-02-17 | 9 | 2022-03-01 | 4 | 44.44% | 224000 | 57910
Orion | Task 3 | McFay | 2022-02-18 | 8 | 2022-03-01 | 0 | 0% | 978000 | 0
Orion | Task 4 | Wood | 2022-02-20 | 7 | 2022-02-28 | 3 | 42.86% | 932000 | 379157
Orion | Task 5 | Ladd | 2022-02-21 | 4 | 2022-02-24 | 1 | 25% | 854000 | 322812
Orion | Task 6 | Hirsch | 2022-02-21 | 6 | 2022-02-28 | 3 | 50% | 81000 | 38461
Orion | Task 7 | Samora | 2022-02-24 | 6 | 2022-03-03 | 5 | 83.33% | 169000 | 136468
Orion | Task 8 | McFay | 2022-02-25 | 4 | 2022-03-02 | 1 | 25% | 61000 | 12078
Orion | Task 9 | Wood | 2022-02-27 | 7 | 2022-03-07 | 3 | 42.86% | 645000 | 273048
Orion | Task 10 | Ladd | 2022-02-17 | 3 | 2022-02-21 | 3 | 100% | 68000 | 64987
Vega | Task 1 | Hirsch | 2022-02-17 | 10 | 2022-03-02 | 5 | 50% | 839000 | 406974
Vega | Task 2 | Samora | 2022-02-21 | 5 | 2022-02-27 | 4 | 80% | 729000 | 487139
Vega | Task 3 | McFay | 2022-02-24 | 7 | 2022-03-06 | 3 | 42.86% | 826000 | 298186
Vega | Task 4 | Wood | 2022-02-26 | 7 | 2022-03-07 | 2 | 28.57% | 895000 | 280583
Vega | Task 5 | Ladd | 2022-02-28 | 3 | 2022-03-02 | 2 | 66.67% | 341000 | 129785
Delta | Task 1 | Hirsch | 2022-03-02 | 9 | 2022-03-14 | 8 | 88.89% | 787000 | 727188
Delta | Task 2 | Samora | 2022-03-02 | 10 | 2022-03-15 | 2 | 20% | 228000 | 47880
Delta | Task 3 | McFay | 2022-02-17 | 4 | 2022-02-22 | 0 | 0% | 147000 | 0
Delta | Task 4 | Wood | 2022-02-19 | 8 | 2022-03-01 | 5 | 62.5% | 338000 | 205123
Delta | Task 5 | Ladd | 2022-02-24 | 10 | 2022-03-09 | 3 | 30% | 857000 | 305949
Delta | Task 6 | Hirsch | 2022-02-25 | 6 | 2022-03-06 | 3 | 50% | 602000 | 322371
Delta | Task 7 | Samora | 2022-02-25 | 4 | 2022-03-02 | 2 | 50% | 990000 | 451440
Alpha | Task 1 | McFay | 2022-02-28 | 8 | 2022-03-09 | 3 | 37.5% | 96000 | 32256
Alpha | Task 2 | Wood | 2022-03-02 | 9 | 2022-03-14 | 4 | 44.44% | 513000 | 226233
Alpha | Task 3 | Ladd | 2022-02-20 | 5 | 2022-02-24 | 3 | 60% | 616000 | 401579
Alpha | Task 4 | Hirsch | 2022-02-19 | 3 | 2022-02-22 | 3 | 100% | 817000 | 807069
Alpha | Task 5 | Samora | 2022-02-21 | 7 | 2022-03-01 | 3 | 42.86% | 372000 | 173166
Alpha | Task 6 | McFay | 2022-02-24 | 10 | 2022-03-09 | 2 | 20% | 50000 | 8400
Alpha | Task 7 | Wood | 2022-02-24 | 10 | 2022-03-09 | 3 | 30% | 807000 | 262679
Alpha | Task 8 | Ladd | 2022-02-24 | 3 | 2022-02-28 | 0 | 0% | 691000 | 0
Formulas:
End Date = WORKDAY.INTL(Project_Data[[#This Row],[Start Date]]-1,Project_Data[[#This Row],[Duration]],7)